## Long Run Day 1(12Jan18)
Date: |  | 2018-01-12 |  |  |  | Shift: | Morning | Night | Overnight |  |  |  | Pauses |  | Stops |  |  | Drifts
Scientist: | [12 empty] | Cleaning | Adjustment | Electronic Communication | PAT Error/adjustment | Feeders | Feeder | RTD | NIR | tablets
Start Time: | 10:00 |  |  | EndTime: | NA
Observations: | Feeding |  | Blending |  | Compression |  |  | RTD/PAT |  | Quality | Guidelines of Events to be captured | To Dos:
8:30 | [7 empty] | Blend NIR - Concentration predicting closer to 10% (previous day closer to 11%). Batch was stopped and NIR reject limts changes to reflect new target (+/- 10%) (KM) |  | Run Start - 8:13 AM - Batch Ref = 20180112_8h7m (PO)
9:00 | [9 empty] | Run restart - 8:43 AM - Batch Ref: 20180112-8h37m using new blend NIR limits (PO)
9:30
10:00 | Avicel PD4 - Communnication alarm resulted in system stop.Same communication error from previous day. System reset and restarted.(PO) | [9 empty] | Major Alarms/Events | add context and interpretation where possible for future analysis by others not on the floor |  |  | Avicel
10:30 | [10 empty] | Diversions | Send Daily Updates
11:00 | [10 empty] | Major Shifts in Trend | Video walkdown from the process for the CDC-50 from the raw material perspective
11:30 | [7 empty] | Blend NIR - Spike in prediction coincides with the scraping of the probe. Also an avicel drum change was made. Evaluate if shift coincides with Drum change.(PO) |  |  | PAT concerns from Mano (Anthony to follow up) | [8 empty] | Blend
12:00 | [10 empty] | Note when and what type of cleaning
12:30 | [7 empty] | Blend NIR - noticable peak in Api concentration- Evaluate if due to buildup of PAI on outlet of screw feeder (PD3) and then falling into feeder manifold- not confirmed (PO) |  |  | Interventions | [8 empty] | Blend
13:00 | [7 empty] | Blend NIR - appearace of concentration drift from the start of campaign 10.4% to 10.7% over 45 min time period.Noticed that RTD and Api feeder do not reflect change. (PO) |  |  | Noticable changes when changing lots of raw material
13:30 | Avicel PD4 - Vacuum hopper ran empty due to void in bulk created by vacuum wand. Poor flow of material did not fill void. Process Stopped. Redistributed material in drum and restart system- issue resolved- (KM) | [9 empty] | Note new lot numbers when added | [5 empty] | Avicel PD4 Bulk
14:00
14:30 | Avicel PD4 - Communnication alarm resulted in process stop.Same communication error from previous day. System reset and restarted.(PO) | [6 empty] | Ejection force high- System Paused but not evidenceof high ejection force. Restarted, no further issue. (AT) | [6 empty] | Avicel PD4
15:00 | Avicel PD4 & PD1- Vacuum hopper ran empty due to void in bulk created by vacuum wand. Poor flow of material did not fill void. Process stopped. Root cause unknown for PD1 (possible blinding of the sensor in the hopper).Redistributed material in drum and restart system- issue resolved- (AT) | [6 empty] | Tablet hardness trending high- compression force was reducing to compensate from 8.0 kp to 7.2 kp. New limits were rquired to be set for force to reflect change. (AT) |  | Blend NIR Step change- Attempted to update limits to reflect offset in prediction. Restarted SynTQ orchestration, which resulted in reinitialization and scraping the probe clean of powder. Blend NIR concentration took a step change down down to ~ 10.1 (AT) | [6 empty] | Avicel PD4 and PD1 Bulk |  |  |  | Hardness
15:30 | Material buildup Mag St PD7 - Noticed some material buildup on outlet of PD7. This may be due to airflow having no where to go from blender 2 and resulting I dust kicking back up towards the feeder. (AT)
16:00 | APAP Feeder Motor speed- Noticed that there was a disturbance registered by RTD. The screw speed drifted to 9000 rpm, then drifted back to normal range (~6500 rpm for 235:1 GR). Paused Run, decision was made to swap out motor for a 63:1. Wet clean was also performed to remove hardened material from the tip of the screws. Restarted Run. Resulting motor speed is now ~1500. Motor current error occured. wet cleaned screws and barrel, then restarted and process ran fine for a few minutes until motor error occured again. Screen was changed from 2mm to 8 mm after noticing material was getting clogged in the 2mm screen.(AT) | [12 empty] | Swapped out motor and screen |  |  |  | APAP
16:30
17:00
17:30
18:00
18:30
19:00 | APAP feeder disturbance (PD3)- Feeder disturbance resulted in diversion event a the press. It was determined that the wrong parameters were uploaded to the feeder after restarting because the CDC recipes that were loaded were not in memory. After correcting the parameters the feeder regained control and process began to make good tablets again.- issue resolved (AT) | [8 empty] | Diversion Event by RTD- see notes on feeding column (AT) | [8 empty] | Diversion
19:30
20:00
20:30
21:00
21:30
22:00
22:30
23:00
23:30
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NIR stands for near-infrared spectroscopy. The NIR measurements are not included in our dataset.

## Long Run Day 2(13Jan18)
Date: |  | 2018-01-12 |  |  | Shift: | Morning | Night | Overnight |  |  |  | Pauses |  | Stops |  |  | Drifts
Scientist: | [11 empty] | Cleaning | Adjustment | Electronic Communication | PAT Error/adjustment | Feeders | Feeder | RTD | NIR | tablets
Start Time:
Observations: | Feeding |  | Blending | Compression |  |  | RTD/PAT |  | Quality | Guidelines of Events to be captured | To Dos:
0:00 | Feeder Manifold Dedusting - System paused to remove excess buildup from feeder outlets- Restarted at 00:24hrs (AG) | [10 empty] | Feeder outlets in blender 1 entrance
0:30
1:00
1:30
2:00 | [6 empty] | NIR probe referencing error - Probe retracted from process for calibration and was not able to reinsert itself due to loss of a bolt (wing nut). Reuslting calibration was incorrect and resulted in a step change of NIR prediction to 22% from 10%. Prediction outside of limits resulted in rejection event until next rereferencing (1 hr frequency)- SA |  | Rejection Event - See NIR Probe referenceing error in RTD/PAT notes | [5 empty] | Verify any stops
2:30
3:00 | [6 empty] | SynTQ failure- Probe Retraction/insertion motor was reset in place. Model limts were increased to allow CDC to restart given the faulty calibration from prior event, but model not active. Restart was not possible without remiving prediction. Process started without NIR prediction untilAM support available. (SA) | [7 empty] | Verify any stops
3:30
4:00
4:30 | Excess powder builup in feeder manifold - APAP feeder (PD3) mesh was changed back to 2 mm to reduce buildup that was occuring from use of 8 mm mesh. This resulted in current alarm with system stop as previously oserved. It was determined that the the new Gear ratio does not have the torque required to overcome the back pressure created by the screen and hence the current was too high. Continued operating near the upper limit of current- (SA) | [14 empty] | APAP
5:00 | APAP (PD3) current alarm - System Stop. Went back to 8mm mesh. Current back to normal level-issue resolved (SA) | [11 empty] | change of outlet mesh |  |  | APAP
5:30
6:00
6:30
7:00
7:30
8:00 | [6 empty] | PAT probe back online - Probe was found stuck in calibration position due to wing nut missing. Found wing nut and reinserted probe manually. PAT back online with accurate predictions - Issue resolved (KM) | [8 empty] | verify any stops
8:30
9:00
9:30 | [6 empty] | PAT retraction/insertion motor failed- predictions reurn to 22%. After reinserting the probe manually the predictions are back to expected values.- issue resolved (PO) | [8 empty] | verify any stops
10:00 | Pit stop (Cleaned feeder barrel) - Powder buildup cleared -(PO) |  |  | Pit Stop Dry clean ECM - There was no requirement driving the decision to clean (system did not shut down) but powder was starting to fall out of the ECM. (KM) | [5 empty] | Major Alarms/Events | add context and interpretation where possible for future analysis by others not on the floor | Pit stop
10:30 | [6 empty] | PAT retraction/insertion motor failed- probe stuck in retract postion after routine scraping. Appears step motor is failing, also possible there is some misalignment of the probe with the housing. (PO) |  |  | Diversions | Send Daily Updates |  |  |  |  | verify any stops
11:00 | [9 empty] | Major Shifts in Trend | Video walkdown from the process for the CDC-50 from the raw material perspective
11:30 | [9 empty] | PAT concerns from Mano (Anthony to follow up)
12:00 | [9 empty] | Note when and what type of cleaning
12:30 | [9 empty] | Interventions
13:00 | [8 empty] | Batch 3 started | Noticable changes when changing lots of raw material
13:30 | Crosscarm feeder (PD5)- communication error ( same as prior communication error) Feeder reset and system restart (AT) | [8 empty] | Note new lot numbers when added |  |  |  | crosscarm PD5
14:00
14:30
15:00 | Avicel feeder (PD1)- communication error ( same as prior communication error) Feeder reset and system restart (AT) | [12 empty] | Avicel PD1
15:30
16:00
16:30 | Feeder barrel cleaning- Manifold into blender 1 was cleaned to ensure no bridging. Accidentally brushed feeer barrel and triggered disturbance (AT) | [7 empty] | RTD Rejection - triggered by brushing the powder from the feeder outlets (AT) |  |  | Cleaning of feeders entering blender 1 |  |  |  |  | Rejection
17:00
17:30 | [6 empty] | NIR Probe calibration failure - Probe retracted and did not re insert into the process. There may be some mis alignment of the probe houseing coupled with the motor failing. Probe was manually inserted, but new predictions are biased at new value. All feeders show operation at expected flow rates. Probe limits set very high to not falsly reject material (AT) |  | RTD Rejection after restart - Process paused to evaluate the NIR probe insertion error. No evidence of actual disturbance by the feeders. There may be a software communication eror between SynTQ and the Press resulting in RTD continuing to process false dtaa during the system pause. (AT) |  |  |  | NIR |  |  |  |  | Rejection
18:00
18:30 | Lactose feeder (PD1)- communication error ( same as prior communication error) Feeder reset and system restart (AT) | [12 empty] | Lactose PD1
19:00 | Crosscarm PD4 - Vacuum hopper ran empty due to void in bulk created by vacuum wand. Poor flow of material did not fill void. Redistributed material in drum and restart system- issue resolved- (AT) | [12 empty] | AcDiSol PD5
19:30
20:00
20:30
21:00 | Mag St feeder cleaning - Noticed feeder was remaining in volumeric modefor extended aount of time after refill. Paused the process to vacuum the buildup around feeder outlet. Restarted system returned to gravimetric operation- issue resolved (AT) | [10 empty] | MgSt |  |  |  |  | Mgst
21:30
22:00
22:30
23:00
23:30 | APAP Feeder Stopped - Tablets Rejected for low potency until back into specification. Apparently the feeder massflow dipped to -8 kg/hr with not change in screw speed.(AG) | [7 empty] | RTD Rejection- After negative APAP disturbance entered the system (AG) | [7 empty] | APAP | rejection

## Long Run Day 3(14Jan18)
Date: |  | 2018-01-12 |  |  |  | Shift: | Morning | Night | Overnight |  |  |  | Pauses |  | Stops |  |  | Drifts
Scientist: | [12 empty] | Cleaning | Adjustment | Electronic Communication | PAT Error/adjustment | Feeders | Feeder | RTD | NIR | tablets
Start Time: | 10:00 |  |  | EndTime: | NA
Observations: | Feeding |  | Blending |  | Compression |  |  | RTD/PAT |  | Quality | Guidelines of Events to be captured | To Dos:
0:00
0:30
1:00
1:30 |  |  |  |  | Tablet Press - Noticed that Tablet Chute actuator was getting hot +/- 57 °C (AG)
2:00 | Lactose Refill failing- 3 x Over the period of 20 min the lacotse refill was empty and material not getting into the feeder. This resulted in a few short stops, which the system automatically started again. Possible blinding of the top up level sensor, knocked the side of the hopper and then restarted the process(AT) |  |  |  | Punch Lubrication Status - Process paused to check status of punch lubrication. Blender 1 & 2 inlet ports vacuumed during pause (AG) | [8 empty] | Press check
2:30
3:00
3:30 | Avicel PD4 Communication error - Process stopped. Acknowledged and restarted (AG) | [13 empty] | Avicel PD4
4:00
4:30
5:00
5:30 | Avicel PD4 Communication error - Process Paused. Acknowledged and restarted (AG) | [13 empty] | Avicel PD4
6:00
6:30 | Avicel PD4 Communication error - Process Paused. Acknowledged and restarted (AG) | [13 empty] | Avicel PD4
7:00
7:30 | HMI running too slow - System paused and restarted | [12 empty] | HMI reset
8:00 | Increase throuhput - from 50 kg/hr to 55 kg/hr and press speed from 53 RPM to 58 RPM. Changes were made in manual as the system does not allow manual changes within a campaign.
8:30
9:00
9:30
10:00 | Pit Stop - Vacuum feeder barrels, API bellows btwn top and feeder. (KM) |  |  |  | Pit Stop - Vacuum ECM | [5 empty] | Major Alarms/Events | add context and interpretation where possible for future analysis by others not on the floor | Pit stop
10:30 | [10 empty] | Diversions | Send Daily Updates
11:00 | [10 empty] | Major Shifts in Trend | Video walkdown from the process for the CDC-50 from the raw material perspective
11:30 | [10 empty] | PAT concerns from Mano (Anthony to follow up)
12:00 | [10 empty] | Note when and what type of cleaning
12:30 | Avicel PD4 Communication error - Process Stopped. Acknowledged and restarted (AG) | [9 empty] | Interventions |  |  |  | Avicel PD4
13:00 | Lactose PD2 Communication error - Process Stopped. Acknowledged and restarted (AG) | [9 empty] | Noticable changes when changing lots of raw material |  |  |  | Lactose PD2
13:30 | [10 empty] | Note new lot numbers when added
14:00
14:30
15:00
15:30
16:00
16:30
17:00
17:30 | Feeder manifold dedusting - Process Paused to clean the manifold into B1. Some bridging observed btwn PD3 & PD4 (AT) | [11 empty] | Feeder outlets in blender 1 entrance
18:00 | Avicel PD4 Communication error - Process Stopped. Acknowledged and restarted (AT) MgSt incompete refill- top up was full, but material was not filling the refill bucket. Knocking the side of the hopper promoted the materialto flow into the refill. (AT) | [13 empty] | Avicel PD4
18:30
19:00
19:30
20:00 | Avicel Refill not complete - Top up seemed full but material was not being delivered to the feeder. (AT)
20:30
21:00
21:30
22:00
22:30 | Avicel PD4 Communication error - Process Stopped. Acknowledged and restarted (AT) | [13 empty] | Avicel PD4
23:00
23:30 | Pit Stop - Vacuum B1 feeder manifold, noticed PD1 had a disturbance due to material build up at outlet into B1 (AG) | [11 empty] | Pit stop (Feeder Manifold)

## Long Run Day 5(16Jan18)
Date: |  | 2018-01-12 |  |  |  | Shift: | Morning | Night | Overnight |  |  |  | Pauses |  | Stops |  |  |  | Drifts
Scientist: | [12 empty] | Cleaning | Adjustment | Electronic Communication | PAT Error/adjustment | Feeders | Press | Feeder | RTD | NIR | tablets
Start Time: | 10:00 |  |  | EndTime: | NA
Observations: | Feeding |  | Blending |  | Compression |  |  | RTD/PAT |  | Quality | Guidelines of Events to be captured | To Dos:
0:00 | Pit Stop - Vacuum B1 & B2 inlet port (AG) | [11 empty] | B1 & B2
0:30 | Feeder Overfilled- After pitstop feeder unstable massflow folowed the overfill. (AG) |  |  |  | Press not starting- Door sensor found loose and taped. Isssue resolved Process started (AG) |  |  |  |  | Blend Potency OOS- after resuming from pit stop OOS occurred. Same issue seen 2 oher instances. (AG) | [9 empty] | Drift after stop
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
5:00
5:30
6:00
6:30
7:00 | Avicel PD2 Communication error - Process Stopped. Acknowledged and restarted (PO) |  | Throughput change to 55 kg/hr | [11 empty] | Avcicel PD2
7:30
8:00
8:30
9:00 |  |  |  |  | Compression Force Compensator - Read/Write difference. Happened 3 consecutive times. Manual change of setpoint fixed the issue. -issue resolved(KM) | [12 empty] | Compression force compensator
9:30
10:00 | Pit Stop - Vacuum B1 & B2 inlet port (AT) |  |  |  | Pit Stop - Vacuum the ECM (AT) | [5 empty] | Major Alarms/Events | add context and interpretation where possible for future analysis by others not on the floor | Pit Stop
10:30 | [10 empty] | Diversions | Send Daily Updates
11:00 | [10 empty] | Major Shifts in Trend | Video walkdown from the process for the CDC-50 from the raw material perspective
11:30 | [10 empty] | PAT concerns from Mano (Anthony to follow up)
12:00 | [10 empty] | Note when and what type of cleaning
12:30 | [10 empty] | Interventions
13:00 | [10 empty] | Noticable changes when changing lots of raw material
13:30 | Avicel PD4 Communication error - Process Stopped. Acknowledged and restarted (AT) | [9 empty] | Note new lot numbers when added |  |  |  | Avcicel PD4
14:00
14:30
15:00
15:30 | Avicel PD2 Communication error - Process Stopped. Acknowledged and restarted (AT) | [13 empty] | Avicel PD2 Communication error - Process Stopped. Acknowledged and restarted (AT)
16:00
16:30 | Lactose Refill failing- Over the period of 16:12 - 16:39 the lacotse refill was empty and material not getting into the feeder. This resulted in a few short stops, which the system automatically started again one one of them. Possible blinding of the top up level sensor, knocked the side of the hopper and then restarted the process(AT) | [15 empty] | Lactose Refill Failure
17:00
17:30
18:00
18:30
19:00
19:30 | Avicel PD1 Communication error - Process Stopped. Acknowledged and restarted (AT) | [13 empty] | Avicel PD1
20:00
20:30
21:00
21:30
22:00
22:30
23:00 | Lactose PD2 Communication error - Process Stopped. Acknowledged and restarted (AG) | [13 empty] | Lactose PD 2
23:30

## Long Run final day(17Jan18)
Date: |  | 2018-01-12 |  |  |  | Shift: | Morning | Night | Overnight |  |  |  | Pauses |  | Stops |  |  |  | Drifts
Scientist: | [12 empty] | Cleaning | Adjustment | Electronic Communication | PAT Error/adjustment | Feeders | Press | Feeder | RTD | NIR | tablets
Start Time: | 10:00 |  |  | EndTime: | NA
Observations: | Feeding |  | Blending |  | Compression |  |  | RTD/PAT |  | Quality | Guidelines of Events to be captured | To Dos:
0:00
0:30
1:00
1:30
2:00
2:30 | Avicel PD4 Communication error - Process Stopped. Acknowledged and restarted (AG) | [13 empty] | Avicel PD4
3:00
3:30
4:00
4:30 | Crosscarm PD5 Communication error - Process Stopped. Acknowledged and restarted (AG) | [13 empty] | Crosscarm PD5
5:00
5:30
6:00
6:30 | Avicel PD4 Communication error - Process Stopped. Acknowledged and restarted (KM) Crosscarm PD5 Communication error - Process Stopped. Acknowledged and restarted (KM) | [13 empty] | Avicel PD4/Crosscarm PD5
7:00
7:30
8:00
8:30
9:00
9:30
10:00 | Avicel PD2 Communication error - Process Stopped. Acknowledged and restarted (AG) | [9 empty] | Major Alarms/Events | add context and interpretation where possible for future analysis by others not on the floor |  |  | Avicel PD2
10:30 | [10 empty] | Diversions | Send Daily Updates
11:00 | Batch Complete | [9 empty] | Major Shifts in Trend | Video walkdown from the process for the CDC-50 from the raw material perspective
11:30 | LHP found to have Broken seal | [9 empty] | PAT concerns from Mano (Anthony to follow up)
12:00 | [10 empty] | Note when and what type of cleaning
12:30 | [10 empty] | Interventions
13:00 | [10 empty] | Noticable changes when changing lots of raw material
13:30 | [10 empty] | Note new lot numbers when added
14:00
14:30
15:00
15:30
16:00
16:30
17:00
17:30
18:00
18:30
19:00
19:30
20:00
20:30
21:00
21:30
22:00
22:30
23:00
23:30

## Long Run Day 4(15Jan18)
Date: |  | 2018-01-12 |  |  |  | Shift: | Morning | Night | Overnight |  |  |  | Pauses |  | Stops |  |  | Drifts
Scientist: | [12 empty] | Cleaning | Adjustment | Electronic Communication | PAT Error/adjustment | Feeders | Feeder | RTD | NIR | tablets
Start Time: | 10:00 |  |  | EndTime: | NA
Observations: | Feeding |  | Blending |  | Compression |  |  | RTD/PAT |  | Quality | Guidelines of Events to be captured | To Dos:
0:00
0:30 | Crosscarm PD5 Communication error - Process Stopped. Acknowledged and restarted (AT) | [13 empty] | Crosscarm PD5
1:00
1:30 | Avicel PD4 Communication error - Process Stopped. Upon restart did not acknowledge the alarm and the system alarmed and stopped due to "mass flow stabilization failure"Acknowledged and restarted (AG) | [13 empty] | Avicel PD4
2:00 | Avicel PD2 Communication error - Process Stopped. Acknowledged and restarted (AG) | [13 empty] | Lactose PD2
2:30
3:00
3:30 | Pit Stop - Vacuum B1 & B2 feeder Manifolds. (AG) | [11 empty] | Feeder manifolds
4:00
4:30
5:00 | Pit Stop - Vacuum B1 & B2 feeder Manifolds. Prior to pit stop it was noticed that PD1 was showing disturbances. Pulled back feeder and saw there was no bridging, but powder beneath the feeder barren and the manifold. (AG) | [11 empty] | Feder Manifolds
5:30
6:00 | Crosscarm PD5 Communication error - Process Stopped. Acknowledged and restarted (AT) | [13 empty] | Crosscarm PD5
6:30 | Totalizer info lost for entire campaign - due to software glitch on the lab CDC. Campaign totals restarted and reset to zero. Feeders stopped at 1048576.000g at slightly diferent times. Progress can still be traced through Mag St Total and or qty API dispensed. This issue is being worked on for the Cramlington system. (PO)
7:00
7:30
8:00
8:30
9:00
9:30
10:00 | Pit Stop - Vacuum feeders (KM) |  |  |  | Pit Stop - Vacuum ECM | [5 empty] | Major Alarms/Events | add context and interpretation where possible for future analysis by others not on the floor | Pit stop
10:30 | New Lot of Avicel in PD4 (Lot 71732C)- Observed change step change of feed factor (PO) | [9 empty] | Diversions | Send Daily Updates | [5 empty] | Avicel PD4
11:00 | [10 empty] | Major Shifts in Trend | Video walkdown from the process for the CDC-50 from the raw material perspective
11:30 | Crosscarm PD5 Communication error - Process Stopped. Acknowledged and restarted (PO) Avicel PD4 Communication error - Process Stopped. Acknowledged and restarted-(KM) NOTE:Copper connections changed to gold on the MSD system, so do not expect the same issues) (PO) | [9 empty] | PAT concerns from Mano (Anthony to follow up) |  |  |  | Avicel PD4 & Crosscarm PD5
12:00 | [10 empty] | Note when and what type of cleaning
12:30 | [10 empty] | Interventions
13:00 | [10 empty] | Noticable changes when changing lots of raw material
13:30 | [10 empty] | Note new lot numbers when added
14:00
14:30 | Lactose PD2 Communication error - Process Stopped. Acknowledged and restarted (AT) | [13 empty] | Lactose PD2
15:00
15:30
16:00
16:30
17:00
17:30 | PD3 Drift of screw speed and feed factor - Paused the process to clean the feeder manifold of B1. After restart, an accidental disturbance during cleaning resulted in PD4 and PD5 thinking it was empty and refilled and overfilled. Process paused. Excess had tp be vacuumed. (AT) | [11 empty] | B1 Manifold |  |  |  |  | APAP
18:00 | [7 empty] | RTD Spike after restart- Similar to previous Spike after restart, there is no evidence it is real and related to a software glitch (AT)
18:30
19:00 | Crosscarm PD5 Vacuum cycle time -Level sensor in the top up was not being triggered after a draw from the bulk, suggesting more material needed to be vacuumed to trigger the level sensor. Increased time to 45 seconds. (AT)
19:30
20:00
20:30
21:00
21:30 | PD3 Drift of screw speed and feed factor - Attempted to brush off material from end of feeder barrel without pausing. (AT) | [16 empty] | APAP Screwspeed
22:00
22:30 | Avicel PD2 Communication error - Process Stopped. Acknowledged and restarted (AG) | [13 empty] | Avicel
23:00
23:30